## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
Customer related user stories:
Adding to the Cart: As a customer, I want to be able to add a dish from the menu to the shopping cart so that it can be a part of my final order. | Given that I am viewing the menu when I click on a dish then I should see a button to add that dish to the shopping cart.
Given that I am viewing a dish, when I click on the "Add to Cart" button, then I should see that dish in the shopping cart.
Given that I add a dish to the shopping cart, when I click on the shopping cart, the dish must visible be in the shopping cart and the order subtotal has incremented by the cost of the dish.
Removing Dish from the Cart: As a customer, I want to be able to remove a dish that is already in the shopping cart so that it will not be a part of my final order. | Given that I am viewing the shopping cart when I wish to delete a dish then a button next to the dish in the shopping cart named "Remove" must exist.
Given that I am viewing the shopping cart when I click "Remove" next to a dish, the dish should be deleted from the shopping cart.
Given that I am viewing the shopping cart, when I delete a dish, the order subtotal must be reduced by the amount of which the dish was worth.
Customer Food Search: As a customer I want to be able to search for a food dish by its partial name on the menu so that I can find it easily. | Given that I am currently on the menu screen when I intend to search for a dish then I must see a search inputfield to type my search in.
Given that I am currently on the menu screen when I have finished typing my search string into the search text box, then I must have a 'Search' button to perform the search
Given that I have entered my search string into the search box on the menu screen, when I click the 'search' button, then I must see a list of dishes whose name consists of the substring that I searched with
Customer Login/Logout: As a customer I want to use my username and password to log in to/log out of the system so that I can browse and order food. | Given the customer already has a username and a password when the customer wants to log in then webpage should provide the corresponding input fields and a button to send the logging in request.
Given the customer sends the correct username and password to the system on a webpage when the customer wants to log in then the customer should be able to log in to the website.
Given the customer sends the wrong username or password to the system when the customer wants to log in then the webpage should indicate that the username or password is not correct.
Given the customer already has a username and a password when the customer wants to log in then webpage should provide the corresponding input fields and a button to send the logging in request.
Given the customer already logged in when the customer is using the system then the customer should see their username on the webpage to indicate their log in/log out status.
Customer Registration: As a customer I want to register my account with a username, a password, a first name, a last name, an email, a phone number, and an address so that I can use the system. | Given the customer wants to register with a username, a password, a first name, a last name, an email, a phone number, and an address when the customer is on the webpage for registration then the webpage should provide the corresponding input fields and a button to send the registration request.
Given there is no customer with the same username exists when the customer enters a username, a password, a first name, a last name, an email, a phone number, and an address on the webpage for registration then the customer should be able to register.
Given there is already a customer with the same username exists when the customer enters a username, a password, a first name, a last name, an email, a phone number, and an address on the webpage for registration then the customer should not be able to register.
Given the customer enters nothing for the username, the password, the first name, the last name, the email, the phone number, or an address when the customer enters a username, a password, a first name, a last name, an email, a phone number, and an address on the webpage for registration then the webpage should indicate the customer missed one or more input fields.
Browse the Menu: As a customer I want to be able to view a list of dishes on the menu so that I can choose to add a dish to my shopping cart | Given that I am logged in when I click on the logo of the website then I am shown a list of dishes.
Given that I am on the menu page when I scroll down then I should be able to see more dishes which are present in the inventory.
Given that I am logged in when I am browsing for dishes then I should be able to see the food dishes in the cart.
Given that I am on the menu page when I select a food item then I should be able to see more detail about the dish which I clicked on. Details such as name, price, description, recipe
Order Creation: As a customer, I want to be able to create an order from the shopping cart so that I can order the food dishes I want. | Given that I am on the shopping cart page when I click the "Checkout" button then I should generate an order that includes all the dishes in the shopping cart.
Given that I am on the shopping cart page when I create an order then my shopping cart should be cleared.
Given that I am on the shopping cart page when I generate an order then the corresponding quantity of the dishes in the order should be removed from the inventory.
Given I have checked out items when I check the order details then it should contain the items of the same quantity which I ordered.
Track History Orders: As a customer, I want to be able to see history orders so that I know what I have ordered before. | Given that I am on the order overview page when I am logged in then I should be able to see a list of orders I ordered before.
Given that I am on the order overview page when I click on a certain order then I should be able to view the detail of the order.
Dish Customization: As a customer I want to customize the ingredients of my dishes so that I can have the flavor I like for the dishes I order. | Given that I am on the custom dish page when I click on the droplists of rice and topping then I should be able to select the rice and topping I want.
Given that I am on the custom dish page when I click on the -/+ button then I should be able to modify the quantity of custom dish I want.
Given that I am on the custom dish page when I click on the "Add to Cart" button then the current custom dish should be add into my shopping cart.
Admin related user stories:
Edit Dishes in Inventory : As an admin I want to edit the dishes in the inventory so that the customer can see the updated information of the dishes. | Given admin wants to edit details of a dish when the admin clicks on the image of the dish then the admin will be navigated to the detail page and all the fields related to the dish should become editable.
Given admin wants to update the details of a dish when the admin edits the quantity of the dish then customers should be able to view the updated quantity of the dish in the menu page. Customer should not be able to add more than the quantity available in the inventory.
Given admin wants to update the details of a dish when the admin edits the description of a dish then customers should be able to view the updated description of the dish in the menu page.
Given admin wants to update the details of a dish when the admin edits the cost of a dish then customers should be able to view the updated cost of the dish in the menu page.
Given admin wants to update the details of a dish when the admin edits the recipe of a dish then customers should be able to view the updated recipe of the dish in the menu page.
Given admin wants to update the details of a dish when the admin edits the image of a dish then customers should be able to view the updated image of the dish in the menu page.
Add Dishes into Inventory: As an admin I want to add the dishes to the inventory so that the customer can see and order the added dishes. | Given that admin wants to Add a dish to the Inventory, when the admin clicks the Add/"+" button then the new dish should become available in the inventory.
Also, The Admin should be able to enter necessary details in the editable field for Dish details.
Remove Dishes from Inventory: As an admin I want to remove the dishes from the inventory so that the customer can not see and order the unavailable dishes. | Given admin wants to delete a dish from the Inventory when the admin clicks the Remove button then the dish should be deleted from the inventory.
Browse Dishes in the Inventory: As an admin I want to see a list of dishes in the inventory so that I can view the details of the dishes. | Given that I am logged in when I am currently on the inventory screen then I must see a list of dishes that are in the inventory.
Given that I am logged in when I am currently on the inventory screen then I can view the detail of a dish by clicking on it.
Search for Dishes in the Inventory: As an admin I want tp search for a food dish by its partial name on the menu so that I can find it easily. | Given that I am currently on the inventory screen when I intend to search for a dish then I must see a search inputfield to type my search in.
Given that I am currently on the inventory screen when I have finished typing my search string into the search text box, then I must have a 'Search' button to perform the search.
Given that I have entered my search string into the search box on the inventory screen, when I click the 'search' button, then I must see a list of dishes whose name consists of the substring that I searched with.
Admin Login/Logout: As an admin I want to use my username and password to log in to/log out of the system so that I can manage the inventory. | Given the admin already has a username and a password when the admin wants to log in then webpage should provide the corresponding input fields and a button to send the logging in request.
Given the admin sends the correct username and password to the system on a webpage when the admin wants to log in then the admin should be able to log in to the website.
Given the admin sends the wrong username or password to the system when the admin wants to log in then the webpage should indicate that the username or password is not correct.
Given the admin hasn't logged in when the admin is using the system then the admin should see a log in button on the webpage to indicate they need to log in.
Given the admin already logged in when the admin is using the system then the admin should see their username on the webpage to indicate their log in/log out status.